# Reading First Implementation Checklist for District Staff--Cohort A Schools--2005-06 School Year

|  | Meetings/Agendas | Deliverables | Visible Support; Communications | School-Wide Model Elements | Administrative Functions |
| --- | --- | --- | --- | --- | --- |
| September | Attend District RF Team meeting Attendees: principals, coaches, district RF team, others Agenda Budget Continuation Grants DIBELS data PD needs Action Plans Reviewing the calendar Scheduling the other meetings | 9/16: School Profiles due to Oregon Reading First Center (ORFC) | Issue “charge”, acknowledgment to RF staff | Support extended learning time for lowest students | Supervision--Provide supervision, support for RF principals which is aligned with RF guidelines |
| October | District Team, Principal, and Mentor Coach attend October 21st Cohort A Leadership training | 10/7: Action Plan Drafts due to ORFC 10/14: Fall CSI maps due to ORFC 10/31: School Action Plans due; Teacher Need Summary due | Make informal visit to RF schools & classrooms: Provide positive feedback/support to staff | Review fall DIBELS reports |  |
| November | Attend District RF Team meeting Attendees: principals, coaches, district RF team, others Agenda: How’s it going? “How Are We Doing?” reports Updates to CSI maps Changes Action Plan review Bringing in the district’s non-RF school leadership |  | Contact with Principals |  |  |
| December |  | 12/6 Fall Fidelity Observations and 5 Minute Observation Summary due 12/16: Winter Fidelity Observation Plan due | Make informal visit to RF schools | Review compliance with terms of grant |  |
| January |  |  | Contact with Principals |  | Budget--Consider support needed by all schools to meet reading needs of students |
| February | Attend district RF Team meeting Attendees: principals, coaches, district RF team, others Agenda: Reviewing January DIBELS Reading Action Plan review PD needs Budget | 2/17: Winter CSI Maps due 2/28 “How Are We Doing?” reports due; Winter Fidelity Observation due; Spring Observation Plan due | Make informal visit to RF schools | Review Winter DIBELS reports |  |
| March | Principal, coach and district team members attend March 3rd Cohort A leadership training session. |  | Contact with Principals |  | Hiring--Support use of RF related criteria for hiring & assigning principals, teachers for RF schools |
| April |  | 4/28: Spring Fidelity Observations due | Informal visit to RF schools | Support planning for summer reading instruction with lowest students |  |
| May | Attend IBR VIII(preferably with each building) - a one day session per building scheduled between 5/30-6/9 |  |  | Support summer training for RF staff as needed Review Spring DIBELS reports |  |
| June/ summer | Attend district RF Team meeting Attendees: principals, coaches, district RF team, others Agenda: Spring, “How Are We Doing? report Reviewing allocation of funds and looking at deadlines for expenditures Data sharing across schools Planning for next year (staffing, schedules, etc.) Discuss Reading Action Plans for 06-07 PD needs for next year - sharing resources | 6/16: Turn all products from IBR VIII deliverables to Oregon Reading First Center--Grade Level RAPs; PD Needs 6/30: Spring “How are we doing?” reports due | Acknowledge RF staff for efforts during the year Attend any end-of-year reading celebrations being held | Support and assure any available summer instructional time for students who need additional reading support Support any summer training that is needed for new or existing staff Review compliance with terms of grant | Share school progress with stakeholders via spring “How are we doing?” reports from district and principals Consider how RF elements can be incorporated into non-RF schools |
| On-going | Maintain contact as needed with those connected to the Reading First program (principal, coach, regional coordinator, superintendent, school board, training and technical assistance providers) Visit RF schools and classrooms periodically; attend a grade level or literacy team meeting to express support and to demonstrate commitment to the success of the program. Inquire about progress and challenges in the RF program and offer support. Review RF program data at the district, school, grade and classroom levels and respond as appropriate. |